## About Hoshin Kanri
1. What is Hoshin Kanri?
Hoshin Kanri is a structured, seven-step strategic planning methodology designed to align an organization’s long-term vision with actionable goals. It ensures that strategic objectives are effectively communicated across all levels of the company and systematically implemented. The process helps businesses focus on key priorities while promoting continuous improvement and engagement among employees.
2. Hoshin X Matrix
The Hoshin X Matrix is a powerful visual tool used in Hoshin Kanri to map strategic objectives, key stakeholders, support steps, and measurable outcomes in a single framework. It offers a customizable approach to goal-setting and execution. In the example provided on monitoring readiness for Laboratory CAP Inspections, the matrix is structured as follows:
Right Side: Lists the hospitals or facilities where tasks are being monitored for readiness.
Left Side: Names the individuals responsible for specific tasks, ensuring accountability.
Upper Side: Outlines the support steps required to achieve readiness, such as training, compliance checks, or resource allocation.
Lower Side: Defines the deliverables (objectives or goals) being tracked, such as accreditation requirements, documentation completion, or procedural adherence.
The Hoshin X Matrix enables organizations to visualize priorities and track progress efficiently.
3. Tracking and Progress Monitoring
To ensure the effective implementation of strategic goals, the matrix includes a tracking system with due dates for each task:
Left Side: Assigns responsibility by labeling individuals accountable for specific deliverables or support steps.
Right Side: Monitors the status of each deliverable or step using clear indicators such as:
"Complete" – Task fully accomplished and meets requirements.
"In Process" – Task is currently underway and progressing toward completion.
"Not Started" – Task has not yet begun, requiring action.
This structured tracking approach enhances visibility, accountability, and overall efficiency in achieving strategic objectives.
For more information and tips on how to apply the Hoshin-Kanri Matrix for Strategic Planning, check out: https://asana.com/resources/hoshin-kanri

## Hoshin Kanri Example
[11 empty] | STATUS | [14 empty] | DUE DATE | Legend
[28 empty] | l | Completed
[28 empty] | m | In Process
[28 empty] | m | Not Started
[10 empty] | LDT Examples Chart Reports | [15 empty] | 2022-07-31
Critical & Corrected Chart Reports
Pathologist Flow Competencies Completed
[10 empty] | Pathologist Serum Protein Electrophoresis Completed | [15 empty] | 2022-07-31
2021 Physician Satisfaction Report in Luci
[10 empty] | Accreditation Mgr MODEL / Regional Account - Change to "NEEDS EDITING" then work through each to mark Inspection Ready (15) | [15 empty] | YAY!!!!
2021 QMS Report Sent for signatures
Update Non-Lab Rosters on CAP website
[10 empty] | Histologist 2022 competency launched in Media Lab - 2020/21 will be in TEAMS; 2022 will lauinch AFTER inspection | On hold
[10 empty] | Cytologist 2022 competency launched in Media Lab - 2020/21 will be in TEAMS; 2022 will lauinch AFTER inspection | On hold
[10 empty] | Path Assist 2022 competency launched in Media Lab - 2020/21 will be in TEAMS; 2022 will lauinch AFTER inspection | On hold
[10 empty] | Biennial P&P Reviews up to date | [15 empty] | 2022-07-31
[10 empty] | BMG Medical Directors |  |  |  |  | m | m
[10 empty] | Ambulatory & Clinical Integration VP/CMO | [5 empty] | m
[10 empty] | Urgent Care Director/CMO | [5 empty] | m
[10 empty] | VBP & BPP Director/CMO | [5 empty] | m
[10 empty] | Deliverables | LABORATORIES | [14 empty] | DUE DATE
Quality Professional D | Quality Professional C | Quality Professional B | Quality Professional A | Respiratory Therapy | POC TMs | Regional Managers | Medical Directors | Facility Managers | Lab Quality Team |  | Facility A | Facility B | Facility C | Facility D | Facility E | Facility F | Facility G | Facility H | Facility I
Lab & Pathology
[10 empty] | 20/21 docs - showers, eye wash, centrifuges | l | l | l | l | l | l | l | l | N/A | l | l | l | l | l | l
[10 empty] | 20/21Water Quality checks: Daily resistivity, Monthly Microbial, and Annual TOC; | l | l | l | l | l | l | l | l | N/A | l | l | l | l | l | l
[10 empty] | Evoqua meter calibration updated | m | m | m | m | l | m | m | l | m
[10 empty] | Corrective Action complete for "Top CAP Std" findings | l | m | l | l | m | l | l | l | l | [6 empty] | 2022-07-31
[10 empty] | 2021 CAP PT: Reviewed, any investigations, attestation signed | l | l | l | l | l | l | l | l | l | [6 empty] | 2022-07-31
[10 empty] | Accreditation Mgr Facility Accounts - Review regional updates | m | m | m | m | m | m | l | m | m | [6 empty] | 2022-07-31
[10 empty] | Acceditation Mgr Facility Accts set to Inspection Ready | m | m | m | m | m | l | l | m | m | m | m | m | m | m | m | 2022-08-29
[10 empty] | Tech Assist 2022 competency completed | N/A | N/A | m | N/A | m | N/A | m | l | N/A | [6 empty] | 2022-08-12
[10 empty] | 2022 Microbiology Gram Stain Slide Competency (ESO Lab) | N/A | m | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | 2022-07-31
[10 empty] | 2022 Microbiology Gram Stain Slide Competency (Hosp Labs) | N/A | N/A | m | m | m | m | l | m | N/A | [6 empty] | 2022-07-31
[10 empty] | Update AHCA lists for Lab Contacts | l | l | l | l | l | l | l | l | l
[10 empty] | Biennial Alternate Site forms updated.(AHCA) | N/A | N/A | N/A | l | N/A | l | l | N/A | N/A | [6 empty] | 2022-05-31
[10 empty] | All delegated duties signed in Media Lab | m | l | l | m | m | l | l | l | m | [6 empty] | Rolling item
[10 empty] | All Pathologist CV, License, Board Certif in Media Lab | l | l | l | l | l | l | l | l | l
[10 empty] | Samples of patient reports (facility specific) Gen Lab | l | l | l | l | l | l | l | l | l
[10 empty] | Check 2021 Interim self inspection document/s to ensure all of the Corrective action is still in place. | m | l | l | m | m | m | l | l | l | [6 empty] | 2022-07-31
[10 empty] | Scan and/or electronic document storage Lab | m | m | m | m | m | m | l | m | m | [6 empty] | 2022-07-15
[10 empty] | Scan and/or electronic document storage Pathology | m | m | m | m | m | m | m | m | m | [6 empty] | 2022-07-15
[10 empty] | Documents copied to System Inspection TEAMS folder | m | m | m | m | m | m | m | m | m | [6 empty] | 2022-07-15
[10 empty] | Review Alinity docs for each lab | l | N/A | l | l | l | l | l | l | N/A
[10 empty] | 2022 CLIA Director Safety Audit | l | l | l | l | l | l | l | l | N/A | m | m | m | m | m | m | 2022-07-31
[10 empty] | 2022 Safety Audits (Hosp Labs) | l | m | m | l | m | l | l | m | m
Point of Care Testing
[10 empty] | Scan and/or electronic document storage (QC, inst, etc.) | N/A | N/A | l | l | m | l | l | l | l | [6 empty] | 2022-07-31
Respiratory Therapy
[10 empty] | Needed foreign equivalencies on file | N/A | N/A | N/A | l | l | l | N/A | l | N/A | [6 empty] | 2022-07-31
[10 empty] | Diplomas in Media Lab Personnel Docs | l | N/A | N/A | l | l | l | l | m | N/A | [6 empty] | 2022-07-31
[10 empty] | Scan and/or electronic document storage (QC, inst, etc.) | l | N/A | N/A | l | l | l | l | m | N/A | [6 empty] | 2022-07-31
Laboratories
Responsibility
Support Steps
2023 CAP Inspection

## Hoshin Kanri Template
[13 empty] | STATUS | [14 empty] | DUE DATE | Legend
[30 empty] | l | Completed
[30 empty] | m | In Process
[30 empty] | m | Not Started
[12 empty] | BMG Medical Directors |  |  |  |  | m | m
[12 empty] | Ambulatory & Clinical Integration VP/CMO | [5 empty] | m
[12 empty] | Urgent Care Director/CMO | [5 empty] | m
[12 empty] | VBP & BPP Director/CMO | [5 empty] | m
[12 empty] | Deliverables | LABORATORIES | [14 empty] | DUE DATE
Responsible Individual M | Responsible Individual L | Responsible Individual K | Responsible Individual J | Responsible Individual H | Responsible Individual G | Responsible Individual F | Responsible Individual E | Responsible Individual D | Responsible Individual C | Responsible Individual B | Responsible Individual A |  | Facility A | Facility B | Facility C | Facility D | Facility E | Facility F | Facility G | Facility H | Facility I
Deliverable Category 1
[22 empty] | l | l | l | l | l | l
[22 empty] | l | l | l | l | l | l
[22 empty] | m | m | m | m | m | m
[22 empty] | m | m | m | m | m | m
Deliverable Category 2
Deliverable Category 3
Laboratories
Responsibility
Support Steps
Strategy/ Goal