## Slide 1: Culture Survey Timeline
  Managers to update and close out 2021 Action Plans in Debriefer Tool DONE
2/3
  Managers to review and submit numbers to Patient Safety for Mapping
  Debriefing Assignments Completed by VPs and submitted to Patient Safety
2/28
  Survey Window Opens
3/21
  Schedule Manager/Director debrief prep meetings to occur between 4/19 -4/29
  Schedule department staff debriefing sessions and enter dates into Debriefer tool
  Schedule post-debrief meetings with unit manager to occur between 05/1-7/31
  Survey closes
3/21-4/15
  Debriefer Training March 31 11am-13pm and April 6 2:30pm-4:30pm
  Survey Results Returned 4-11
  Platform Training Results Access Webinar 4/12 12-1pm
4/18 -4/29
  Hold Debrief prep meetings and complete slides
  Executive Leadership Briefing Webinar 4/26 12-1pm
  Debriefing Your Survey Results Training Webinar 4/28 12-1pm
5/2-7/30
  Hold Staff Debriefings and enter notes into the Debriefing tool
  VPs to hold Divisional touchpoints
  Hold post-debrief meetings with Unit Manager/Director
9/2
  Managers to enter Action Plans into the Debriefing tool
9/5-12-5
  Managers to update and close out 2022 Action Plans in Debriefer Tool